## Sheet1
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
s1 | s1 | US-001 | CV introduction: Principles Of Image Processing, Object Detection, CNNs Overview | MUST HAVE | None | Deepak Kumar | 3- Completed
s1 | s1 | US-002 | OCR introduction Intoduction To Text Extraction, Text Recognizer | MUST HAVE | None | Deepak Kumar | 3- Completed
s2 | s2 | US-003 | ANPR implementation : Reading & Processing Of The Pre-Trained Images & Video And Extracting Text From Them To Detect Number Plates | MUST HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s2 | s2 | US-004 | YOLO models Training: Training Various YOLO Models for detecting the Number Plates | COULD HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s2 | s2 | US-005 | Image Processing :Training Of Images In Various Formats Like Gray Scale, Normal, Blurred & Extract The Text From Them | MUST HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s2 | s2 | US-006 | Video Processing :Reading & Capturing Of The Frames In The Video & Annotate It To Detect The Vechicles In It By Different Formats Like Cars, Buses, Trucks, etc.. | MUST HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s3 | s3 | US-007 | Building the ATCC System :Training and testing classification models, Develop a deep learning-based vehicle classification model (e.g., cars, trucks, motorcycles) | MUST HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s3 | s3 | US-008 | Training and testing classification models :Training And Testing Of Various Vehicle Classification Models like Cars, Motercycles,Trucks etc… | SHOULD HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s3 | s3 | US-009 | Developing a deep learning based vehicle classification models :- Developing Of A Deep Learing-Based Classification Model Based On The Trained & Tested Vechicle Classification Models (e.g., cars, trucks, motorcycles) | MUST HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s3 | s3 | US-010 | Creating A Live Object Tracker :Creating a Live Tracker Feed to Track The Objects(ie; Vehicles) throught the System Camera Or Web Cam | COULD HAVE | A Working System Camera Or Web Cam,Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s3 | s3 | US-011 | Sorting & Adding Missing Value :Sorting Of the Detected Vehicles and its Number Plates, Frame IDs Into a Csv File For Better Classification And Add Missing Values Like Frame IDs In the Csv File Through Data Processing | MUST HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s3 | s3 | US-012 | Visualization :Visualize The Number Plates And Vechicles In The Traffic Video Using The Csv File | MUST HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s4 | s4 | US-013 | System Integration and Real-Time Optimization :Combining ANPR and ATCC systems into a cohesive platform and optimizing for real-time performance | MUST HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s4 | s4 | US-014 | System integration for real-world applications :Successful integration of ANPR and ATCC with optimized performance and real-time processing capabilities. | MUST HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s4 | s4 | US-015 | Implementing optimizations to improve model inference speed and accuracy. | MUST HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed
s4 | s4 | US-016 | Classifying the Vehicles into Various Classes Such As Cars, Buses, Motercycles, Trucks, etc... | MUST HAVE | Python Libraries[OpenCV, OCR, Easy Ocr, Tesseract, Ultralytics,etc..] & Various Yolo Models | Deepak Kumar | 3- Completed

## Sheet2
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 138 | 12 | 12 | 11 | 17 | 15 | 6 | 0 | 12 | 14 | 10 | 14 | 14 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Principles Of Image Processing, Object Detection | 2024-12-04 | 2024-12-04 | Deepak Kumar | Others | 3- Completed | 5 | Day 1: 2; Day 2: 2; Day 3: 1
US-001 | TID-02 | CNNs Overview | 2024-12-05 | 2024-12-05 | Deepak Kumar | Others | 3- Completed | 4 | Day 4: 2; Day 5: 2
US-002 | TID-01 | Intoduction to Text Extraction | 2024-12-06 | 2024-12-06 | Deepak Kumar | Others | 3- Completed | 6 | Day 8: 3; Day 9: 2; Day 10: 1
US-002 | TID-02 | Intoduction To text Recognization | 2024-12-09 | 2024-12-09 | Deepak Kumar | Others | 3- Completed | 4 | Day 11: 3; Day 12: 1
SPRINT 2 BACKLOG
US-003 | TID-01 | Reading & Processing Of The Pre-Trained Images | 2024-12-11 | 2024-12-12 | Deepak Kumar | Build | 3- Completed | 4 | Day 1: 4
US-003 | TID-02 | Reading & Processing Of The Pre-Trained Video | 2024-12-13 | 2024-12-13 | Deepak Kumar | Build | 3- Completed | 5 | Day 2: 5
US-003 | TID-03 | Extracting Text From Them To Detect Number Plates | 2024-12-16 | 2024-12-17 | Deepak Kumar | Build | 3- Completed | 4 | Day 3: 4
US-004 | TID-01 | Training Of Various Yolo Models For Detecting The Number Plates | 2024-12-18 | 2024-12-19 | Deepak Kumar | Coding | 3- Completed | 5 | Day 4: 5
US-005 | TID-01 | Training Of Images In Gray Scale Format | 2024-12-20 | 2024-12-23 | Deepak Kumar | Coding | 3- Completed | 5 | Day 5: 5
US-005 | TID-02 | Training Of Images In Normal Format | 2024-12-24 | 2024-12-26 | Deepak Kumar | Coding | 3- Completed | 3 | Day 8: 3
US-005 | TID-03 | Training Of Images In Blurred Format | 2024-12-27 | 2024-12-30 | Deepak Kumar | Coding | 3- Completed | 4 | Day 9: 4
US-005 | TID-04 | Extracting Text From The Trained Image | 2024-12-31 | 2024-12-31 | Deepak Kumar | Coding | 3- Completed | 4 | Day 10: 4
US-006 | TID-01 | Reading & Capturing Of The Frames In The Video | 2025-01-02 | 2025-01-02 | Deepak Kumar | Coding | 3- Completed | 5 | Day 11: 5
US-006 | TID-02 | Annotate It To Detect The Vechicles In It By Different Formats Like Cars, Buses, Trucks, etc.. | 2025-01-03 | 2025-01-06 | Deepak Kumar | Design | 3- Completed | 6 | Day 12: 6
SPRINT 3 BACKLOG
US-007 | TID-01 | Overview & Building the ATCC System | 2025-01-07 | 2025-01-07 | Deepak Kumar | Build | 3- Completed | 3 | Day 1: 3
US-008 | TID-01 | Training Of Various Vehicle Classification Models | 2025-01-08 | 2025-01-09 | Deepak Kumar | Coding | 3- Completed | 6 | Day 2: 3; Day 3: 3
US-008 | TID-02 | Testing Of Various Vehicle Classification Models | 2025-01-10 | 2025-01-13 | Deepak Kumar | Coding | 3- Completed | 4 | Day 4: 4
US-009 | TID-01 | Develop a deep learning-based vehicle classification models | 2025-01-14 | 2025-01-15 | Deepak Kumar | Design | 3- Completed | 6 | Day 5: 4; Day 6: 2
US-010 | TID-01 | Creating A Live Tracker | 2025-01-16 | 2025-01-17 | Deepak Kumar | Coding | 3- Completed | 3 | Day 8: 3
US-011 | TID-01 | Sorting Of the Detected Vehicles and its Number Plates, Frame IDs Into a Csv File For Better Classification | 2025-01-20 | 2025-01-20 | Deepak Kumar | Design | 3- Completed | 6 | Day 9: 6
US-011 | TID-02 | Add Missing Values Like Frame IDs In the Csv File Through Data Processing | 2025-01-21 | 2025-01-21 | Deepak Kumar | Coding | 3- Completed | 5 | Day 10: 5
US-012 | TID-01 | Visualize The Number Plates And Vechicles In The Traffic Video Using The Csv File | 2025-01-23 | 2025-01-23 | Deepak Kumar | Coding | 3- Completed | 5 | Day 11: 3; Day 12: 2
SPRINT 4 BACKLOG
US-013 | TID-01 | Combining ANPR and ATCC systems into a cohesive platform | 2025-01-24 | 2025-01-24 | Deepak Kumar | Integration Test | 3- Completed | 9 | Day 1: 3; Day 2: 2; Day 3: 3
US-013 | TID-02 | Optimizing for real-time performance | 2025-01-27 | 2025-01-27 | Deepak Kumar | Design | 3- Completed | 6 | Day 4: 6
US-014 | TID-01 | Successful integration of ANPR and ATCC with optimized performance and real-time processing capabilities. | 2025-01-28 | 2025-01-28 | Deepak Kumar | System Test | 3- Completed | 8 | Day 5: 4; Day 6: 4
US-015 | TID-01 | Implementing optimizations to improve model inference speed and accuracy. | 2025-01-29 | 2025-01-29 | Deepak Kumar | Coding | 3- Completed | 8 | Day 8: 3; Day 9: 2; Day 11: 3
US-015 | TID-02 | Ensuring smooth data flow between ANPR and ATCC for dynamic decision-making |  |  | Deepak Kumar | Integration Test | 3- Completed | 5 | Day 12: 5

## Sheet3
Sprint | Day | Impediments | Action Taken
s1 | 1 | Introduction to Computer Vision | Learning the bascis of Computer Vision
s1 | 8 | Introduction to OCR | Learning About Optical Character Recognition
s2 | 16 | Introduction & Implementation Of ANPR | Implementing APNR practically
s2 | 19 | Training Of Various Yolo Models | Training Of Various YOLO Models For Vechicle Detection
s2 | 23 | Processing Of Images | Reading & Processing Of Pre-Trained Images In Various Formats To Extract Text From Them To Detect Number Plates
s2 | 25 | Processing Of Video's | Reading & Processing Of Pre-Trained Video's Into Frames & Annotate Them To Detect The Vechicles In It
s3 | 29 | Training and testing classification model | Training and testing Various Vehicle Classification Models like Cars, Trucks, Buses etc…
s3 | 31 | Develop a deep learning-based vehicle classification models | Developing Of A Deep Learing-Based Classification Model Based On The Trained & Tested Vechicle Classification Models (e.g., cars, trucks, motorcycles)
s3 | 36 | Creating A Live Objects Tracker | Creating Of A Live Tracker Feed To Tracker The Objects(ie; Vehicles) Through The System Camera Or Web Cam
s3 | 37 | Sorting & Adding Missing Value | Sorting Of the Detected Vehicles and its Number Plates, Frame IDs Into a Csv File For Better Classification And Add Missing Values Like Frame IDs In the Csv File Through Data Processing
s3 | 38 | Visualization | Visualize The Number Plates And Vechicles In The Traffic Video Using The Csv File
s4 | 43 | System Integration and Real-Time Optimization | Combining ANPR and ATCC systems into a cohesive platform
s4 | 48 | System integration for real-world applications | Successful integration of ANPR and ATCC with optimized performance and real-time processing capabilities.
s4 | 51 | Performance optimization techniques | Implementing optimizations to improve model inference speed and accuracy.
s4 | 58 | Classification | Classifying The Vehicles Into Various Classes Such As Cars, Buses, Motercycles, Trucks, etc...

## Sheet4
Sprint | Day | Impediments | Action Taken
s1 | 1 | Introduction to Computer Vision | Learning the bascis of Computer Vision
s1 | 8 | Introduction to OCR | Learning About Optical Character Recognition
s2 | 16 | Introduction & Implementation Of ANPR | Implementing APNR practically
s2 | 19 | Training Of Various Yolo Models | Training Of Various YOLO Models For Vechicle Detection
s2 | 23 | Processing Of Images | Reading & Processing Of Pre-Trained Images In Various Formats To Extract Text From Them To Detect Number Plates
s2 | 25 | Processing Of Video's | Reading & Processing Of Pre-Trained Video's Into Frames & Annotate Them To Detect The Vechicles In It
s3 | 29 | Training and testing classification model | Training and testing Various Vehicle Classification Models like Cars, Trucks, Buses etc…
s3 | 31 | Develop a deep learning-based vehicle classification models | Developing Of A Deep Learing-Based Classification Model Based On The Trained & Tested Vechicle Classification Models (e.g., cars, trucks, motorcycles)
s3 | 36 | Creating A Live Objects Tracker | Creating Of A Live Tracker Feed To Tracker The Objects(ie; Vehicles) Through The System Camera Or Web Cam
s3 | 37 | Sorting & Adding Missing Value | Sorting Of the Detected Vehicles and its Number Plates, Frame IDs Into a Csv File For Better Classification And Add Missing Values Like Frame IDs In the Csv File Through Data Processing
s3 | 38 | Visualization | Visualize The Number Plates And Vechicles In The Traffic Video Using The Csv File
s4 | 43 | System Integration and Real-Time Optimization | Combining ANPR and ATCC systems into a cohesive platform
s4 | 48 | System integration for real-world applications | Successful integration of ANPR and ATCC with optimized performance and real-time processing capabilities.
s4 | 51 | Performance optimization techniques | Implementing optimizations to improve model inference speed and accuracy.
s4 | 58 | Classification | Classifying The Vehicles Into Various Classes Such As Cars, Buses, Motercycles, Trucks, etc...

## Sheet5
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | s1 | 2024-12-04 | 2024-12-09 | Deepak Kumar | Introduction To Computer Vision | Introduction To OCR | Overview Of The Topics | Clarifying the Doubts With Mentor
2 | s2 | 2024-12-11 | 2025-01-06 | Deepak Kumar | Overview & Implementing ANPR& ATCC | Reading & Processing Of The Pre-Trained Images & Video | Yolo Model Training | Extracting Text from them the detect Number Plates using Processed Images & Videos
3 | s3 | 2025-01-07 | 2025-01-23 | Deepak Kumar | Developed a Deep Learning based Vehicle Classification Models | Sorting & Adding Missing Value | Visualization | Detecting Vehicles and their number plates from the Vidoes
4 | s4 | 2025-01-24 | 2025-01-29 | Deepak Kumar | System Integration and Real-Time Optimization | Performance optimization techniques | Classification | Classifiying The Objects(ie; Vehicles and Its Number Plates) In The Processed Videos